## Worksheet
Project Timeline – Financial Management (Freelancer Style)
Task | Owner | Start Date | End Date | Status | Budget (USD) | Progress (%) th>
Financial Planning & Analysis | Jane Doe | 2024-03-01 | 2024-03-15 | In Progress | 1,500.00 | 65%
Expense Tracking Setup | Alex Chen | 2024-03-16 | 2024-04-10 | Pending | 800 | —%
Budget Approval Workflow | Sarah Kim | 2024-04-11 | 2024-04-25 | Not Started | 1,200.00 | —%
Monthly Financial Reporting | Marcus Lee | 2024-05-01 | 2024-11-30 | Scheduled | 3,000.00 | —%
Repayment Strategy Development | Lena Patel | 2024-06-01 | 2024-08-31 | Not Started | 2,500.00 | —%
Cash Flow Forecasting | Daniel Wang | 2024-09-01 | 2024-10-31 | Pending | 1,800.00 | —%