## Worksheet
Project Name | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Progress (%) | Owner | Next Milestone
Financial System Upgrade | 2024-03-01 | 2024-06-30 | In Progress | 150,000 | 98,567 | 72% | Jane Smith | Q2 Audit Completion
Annual Budget Review | 2024-04-15 | 2024-05-31 | On Track | 75,000 | 68,342 | 91% | Michael Brown | Draft Final Budget Approved
Expense Reporting Automation | 2024-05-01 | 2024-08-31 | Planned | 120,000 | - | - | Sarah Lee | Phase 1 Launch (Q3)
Cost Center Reallocation | 2024-06-01 | 2024-10-31 | Pending Approval | 85,000 | - | - | David Chen | Management Review Meeting (Q3)