## Worksheet
Project Phase | Start Date | End Date | Responsible Party | Budget Allocation ($) | Status
Feasibility Study | 2024-03-01 | 2024-03-15 | Finance Manager | 2,500 | Completed
Business Planning | 2024-03-16 | 2024-04-30 | Project Lead | 5,000 | In Progress
Resource Acquisition | 2024-05-01 | 2024-05-31 | Operations Director | 8,000 | Planned
Pilot Launch | 2024-06-01 | 2024-07-31 | Marketing Team | 15,000 | Not Started
Full Scale Operations | 2024-08-01 | 2024-10-31 | CEO & CFO | 35,000 | Scheduled