## Worksheet
Project Phase | Start Date | End Date | Budget (USD) | Responsible Team | Key Deliverables | Status
Market Research | 2024-03-01 | 2024-03-31 | 15,000 | Product Strategy Team | Feasibility Report, Target Audience Profile | On Track
Product Design | 2024-04-01 | 2024-05-15 | 35,000 | Design & UX Team | Wireframes, High-Fidelity Prototypes | In Progress
Development Phase | 2024-05-16 | 2024-08-31 | 120,000 | Engineering Team | MVP Build, API Integration | Planned
Beta Testing & Feedback | 2024-09-01 | 2024-10-31 | 25,000 | Product & QA Team | User Feedback Summary, Bug Report v1.0 | Not Started
Launch & Marketing | 2024-11-01 | 2024-12-31 | 75,000 | Marketing & Sales Team | Launch Campaign, User Onboarding Kit | Planned