## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Budget (USD) | Actual Cost (USD) | Progress (%)
Project Initiation | 2024-03-01 | 2024-03-15 | Finance Director | Completed | 10,000 | 9,800 | 100%
Feasibility Study | 2024-03-16 | 2024-04-10 | Business Analysts | In Progress | 15,000 | 12,500 | 83%
Budget Finalization | 2024-04-11 | 2024-05-01 | Finance Manager | Planned | 25,000 | 0 | 0%
Resource Allocation | 2024-05-02 | 2024-05-31 | HR & Operations Team | Not Started | 8,500 | 0 | 0%
Financial Reporting Setup | 2024-06-01 | 2024-07-31 | Accounting Officer | Scheduled | 5,000 | 0 | 0%