## Worksheet
Week | Project Phase | Budget Allocated (USD) | Actual Expenditure (USD) | Variance (USD) | Status | Responsible Person
Week 1 | Project Initiation & Planning | $25,000 | $23,500 | +$1,500 (Under Budget) | On Track | John Smith
Week 2 | Requirements Gathering | $30,000 | $28,750 | +$1,250 (Under Budget) | On Track | Emily Davis
Week 3 | Design & Prototyping | $45,000 | $44,200 | +$800 (Under Budget) | On Track | Michael Lee
Week 4 | Development Phase (Phase 1) | $60,000 | $59,800 | +$200 (Under Budget) | On Track | Sarah Kim
Week 5 | Testing & Quality Assurance | $35,000 | $36,100 | -$1,100 (Over Budget) | At Risk | David Wong
Week 6 | Deployment Planning | $20,000 | $19,500 | +$500 (Under Budget) | On Track | Lena Patel