## Worksheet
Project Name | Budget (USD) | Start Date | End Date | Current Status | Actual Spend (USD) | Variance (USD) | Responsible Person | Next Review Date
Website Redesign | 50,000 | 2024-03-15 | 2024-06-30 | On Track | 42,500 | +7,500 | Sarah Johnson | 2024-05-15
Marketing Campaign | 30,000 | 2024-04-10 | 2024-07-15 | Over Budget | 34,800 | +4,800 | Mike Chen | 2024-06-15
App Development Phase 2 | 100,000 | 2024-05-01 | 2024-11-30 | In Progress | 68,000 | +32,000 | Lisa Park | 2024-08-15
Customer Support Upgrade | 20,000 | 2024-06-15 | 2024-10-31 | Pending Approval | 0 | 0 | David Wilson | 2024-07-15