## Worksheet
Project Name | Budget (USD) | Actual Spend (USD) | Remaining Budget (USD) | Start Date | End Date | Status | Primary Contact | Department | Financial Review Date | Notes
Website Redesign Project | 50,000 | 42,350 | 7,650 | 2024-01-15 | 2024-03-31 | On Track | Sarah Johnson | Marketing | 2024-02-10 | Updated design mockups approved.
New CRM Implementation | 120,000 | 85,400 | 34,600 | 2024-02-18 | 2024-05-30 | In Progress | Michael Chen | IT Operations | 2024-03-15 | Integration with existing systems delayed by 2 weeks.
Employee Training Program | 30,000 | 28,750 | 1,250 | 2024-03-01 | 2024-04-30 | On Track | Lisa Patel | HR Development | 2024-03-25 | All modules completed; attendance above target.
Cloud Migration Initiative | 200,000 | 145,200 | 54,800 | 2024-01-30 | 2024-11-30 | Delayed | David Kim | IT Infrastructure | 2024-04-10 | Vendor issues; migration postponed to Q3.