## Worksheet
Project ID | Project Name | Budget (USD) | Start Date | End Date | Current Status | Allocated Funds (USD) | Remaining Budget (USD) | Responsible Team | Financial Review Date
PRJ-2023-001 | Infrastructure Upgrade | 500,000.00 | 2023-11-15 | 2024-03-31 | In Progress | 325,678.50 | 174,321.50 | Engineering & Finance Team | 2024-01-10
PRJ-2023-002 | Customer Experience Enhancement | 250,000.00 | 2023-12-01 | 2024-11-30 | Pending Approval | 89,543.75 | 160,456.25 | Marketing & Product Team | 2024-01-15
PRJ-2023-003 | Data Analytics Platform Implementation | 750,000.00 | 2024-01-18 | 2024-12-31 | On Hold (Pending Vendor Approval) | 356,890.00 | 393,110.00 | Data Science Team | 2024-02-12
PRJ-2023-004 | Cloud Migration Strategy | 400,000.00 | 2023-11-30 | 2024-12-15 | Completed | 400,000.00 | 0 | IT Operations Team | 2024-11-30
Financial Summary |  |  |  |  | Total Budget (USD)
[5 empty] | $1,900,000.00 | $1,248,737.25 | $651,262.75