## Worksheet
Project ID | Project Name | Budget (USD) | Actual Spend (USD) | Remaining Budget (USD) | Status | Start Date | End Date | Responsible Team | Financial Review Date
PRJ-001 | Digital Transformation Initiative | 500,000 | 385,476 | 114,524 | On Track | 2023-03-01 | 2024-09-30 | IT & Strategy Team | 2024-05-15
PRJ-002 | Customer Experience Upgrade | 300,000 | 298,654 | 1,346 | On Track | 2023-05-01 | 2024-07-31 | Customer Success Team | 2024-06-05
PRJ-003 | Cloud Infrastructure Migration | 750,000 | 689,234 | 60,766 | On Track | 2023-08-15 | 2024-10-31 | Engineering Team | 2024-08-10
PRJ-004 | Marketing Campaign Expansion | 250,000 | 238,956 | 11,044 | On Track | 2023-09-05 | 2024-11-30 | Marketing Team | 2024-09-18
PRJ-005 | HR System Implementation | 180,000 | 175,324 | 4,676 | On Track | 2023-10-01 | 2024-03-31 | HR Operations Team | 2024-08-30