## Worksheet
Project Name | Budget (USD) | Start Date | End Date | Current Status | Actual Spend (USD) | Variance (USD) | Responsible Team
Website Redesign | 50,000 | 2024-01-15 | 2024-03-31 | On Track | 42,500 | +7,500 | Digital Marketing Team
Client Onboarding System | 75,000 | 2024-02-01 | 2024-05-30 | In Progress | 38,900 | +16,100 | IT Operations Team
Financial Reporting Module | 100,000 | 2024-03-10 | 2024-12-31 | Planned | 0 | 0 | Finance & Analytics Team