## Worksheet
Task ID | Task Description | Assigned To | Priority Level | Due Date | Status | Budget Allocation ($) | Actual Spend ($) | Variance ($) | Progress (%) | Notes
FM-T001 | Monthly financial statement preparation | Jane Smith | High | 2023-10-31 | Completed | 5,000.00 | 4,950.00 |  | 50 | 100% | No outstanding issues.
FM-T002 | Quarterly expense review and forecasting | Michael Chen | Moderate | 2023-11-15 | In Progress | 8,000.00 | 4,200.00 | +3,800.00 | 55% | Revising vendor cost assumptions.
FM-T003 | Annual audit preparation | Sarah Johnson | High | 2024-01-30 | Pending Assignment | 15,000.00 | 0 | -15,000.00 | 2% | Audit team to be finalized.
FM-T004 | Review of departmental cost centers | Laura Taylor | Low | 2023-12-10 | Not Started | 3,500.00 | 0 | -3,500.00 | 1% | Data collection phase pending.