## Worksheet
Goal Identifier | Goal Purpose | Target Date | Current Status | Progress (%) | Responsible Party | Resources Allocated | Key Milestones | Risks & Dependencies | Review Frequency
G-001 | Develop and launch a new product line in Q3 | 2024-09-30 | In Progress | 65% | Product Manager, Marketing Team | $150,000, 5 FTEs | Milestone 1: Design complete (May), Milestone 2: MVP ready (July) | Supply chain delays; market demand uncertainty | Monthly
G-002 | Improve customer retention by 25% within one year | 2025-12-31 | Planned | 30% | Customer Success Lead, Data Analytics Team | $80,000, CRM software upgrade | Milestone 1: Retention analysis (June), Milestone 2: Pilot program (Q4) | Customer churn rate rising; low engagement in segment B | Quarterly
G-003 | Expand into European market by end of 2024 | 2024-12-31 | Not Started | 0% | International Operations Director, Sales Team | $300,000, market research budget | Milestone 1: Market feasibility study (Apr), Milestone 2: Pilot launch (Oct) | Regulatory hurdles; local competition intensity | Bi-monthly
G-004 | Reduce operational costs by 15% in FY24 | 2024-12-31 | In Progress | 45% | Finance Director, Operations Manager | $75,000 savings initiative fund, process optimization team | Milestone 1: Audit complete (Mar), Milestone 2: Automation implemented (Jul) | Employee resistance; legacy system limitations | Monthly