## Worksheet
Goal ID | Goal Title | Objective | Target Date | Current Status | Responsible Party | Progress (%) | Resources Required | Risks & Challenges | Key Milestones | Review Date
G-001 | Increase Market Share by 15% | Expand customer base through targeted digital campaigns and loyalty programs. | 2025-06-30 | Active | Marketing Team | 45% | Budget $100K, Digital Ads, Analytics Tools | Ad fatigue, competition increase | Launch Campaign (Q2), Feedback Survey (Q3) | 2025-04-15
G-002 | Improve Product Quality Rating | Enhance user experience by reducing defect rates and improving feedback response time. | 2025-09-15 | Planning | Quality Assurance & R&D | 20% | Test equipment, QA training, new inspection protocol | Supply chain delays, testing bottlenecks | Phase 1 Testing (Q2), Final Review (Q4) | 2025-05-20
G-003 | Expand to New Geographic Market | Enter the European market with localized product offerings and compliance strategy. | 2026-03-31 | Pending Approval | Global Strategy Team | 10% | Market research, legal compliance, localization funds | Regulatory hurdles, cultural differences | Feasibility Study (Q3), Pilot Launch (Q1 2026) | 2025-06-10