## Worksheet
Week | Goal | Target Outcome | Current Status | Progress (%) | Actions Taken | Next Steps | Owner
Week 1 | Define quarterly objectives | Establish clear, measurable goals aligned with business strategy | Completed initial goal identification | 70% | Workshop with team to align priorities | Finalize and document all goals by end of week 2 | John Smith
Week 2 | Develop asset tracking system | Create a standardized process for monitoring and updating asset inventory | System drafted and reviewed | 50% | Conducted stakeholder feedback session | Finalize system design and conduct training in week 3 | Sarah Lee
Week 3 | Conduct asset inventory audit | Verify physical assets against digital records | Partial audit completed (50%) | 40% | Scheduled site visits and data collection | Complete full audit and update master list by week 4 | Michael Brown
Week 4 | Implement tracking dashboard | Deploy real-time visibility for asset utilization and maintenance status | Dashboard in development | 20% | UI/UX mockups approved by leadership | Launch dashboard with access control settings by week 5 | Lisa Chen
Week 5 | Train team on new tracking process | All team members proficient in using the asset system | Training sessions scheduled | 0% | Develop training materials and schedule sessions | Conduct follow-up assessment to verify competency | David Taylor