## Worksheet
Goal | Target Date | Current Progress | Budget / Resources Allocated | Status (Pending/On Track/Overrun) | Actions Required
Launch New Marketing Campaign | 2024-06-30 | 70% completed (content drafted) | $5,000 | On Track | Finalize creative assets by May 15
Increase Customer Retention Rate | 2024-09-30 | 30% completed (survey launched) | $12,000 | Pending | Review survey results and implement feedback by July 15
Expand Product Line to Europe | 2024-12-31 | 0% completed (market research ongoing) | $30,000 | Pending | Finalize market analysis report by August 31
Reduce Operational Costs by 10% | 2024-11-30 | 50% completed (supplier negotiations in progress) | $8,500 | On Track | Finalize cost-saving proposals by October 15