## Worksheet
Week | Goal | Objective | Key Activities | Success Metrics | Responsible Person | Deadline | Progress Status
Week 1 | Define Company Vision & Core Values | Establish a clear direction for the business within the next quarter. | Conduct stakeholder interviews, draft vision statement, review market trends. | Positive feedback from key stakeholders; vision document finalized. | CEO | 2024-04-05 | On Track
Week 2 | Identify Target Market Segments | Determine which customer groups will be prioritized for product development. | Survey analysis, competitor benchmarking, data mining of customer behavior. | 3+ validated market segments with clear demographic profiles. | Marketing Director | 2024-04-12 | In Progress
Week 3 | Develop Product Roadmap | Create a phased product development plan aligned with market needs. | Workshop sessions, prioritize features, draft timelines and dependencies. | Product roadmap approved by leadership; timeline set. | CFO & Product Manager | 2024-04-19 | Pending Input
Week 4 | Launch Marketing Campaign Pilot | Test a targeted campaign with a subset of the identified market segment. | Create ad copy, design assets, deploy in social media channels. | 15% engagement increase; measurable conversion rate improvement. | Marketing Team | 2024-04-26 | Not Started
Week 5 | Review Q1 Performance & Adjust Goals | Evaluate achievements and make data-driven adjustments for Q2. | Analyze KPIs, conduct team review, update goals. | Performance report submitted; revised goals approved by leadership. | Operations Head | 2024-05-03 | Planned