## Worksheet
Business Goal Setting - Planning View
Goal Number | Goal Description | Purpose / Objective | Target Date | Owner (Name) | Status
1 | Expand Market Presence in North America | To increase brand visibility and customer acquisition in the U.S. and Canada by 30% within one year. | 2025-12-31 | John Doe | Pending Approval | Market research completed; 5 new channels identified. | Conduct regional marketing campaigns; launch digital ads on Google and Meta.
2 | Improve Customer Retention Rate | To increase customer retention by 15% through improved service delivery and loyalty programs. | 2025-09-30 | Sarah Kim | In Progress | Retention rate: 78% → Target: 90% | Launch loyalty rewards program; train customer service team on retention strategies.
3 | Reduce Operational Costs by 10% | To optimize supply chain and reduce overhead costs through automation and vendor renegotiation. | 2025-06-30 | Michael Reed | On Track | Cost reduction achieved: 7% in Q1; projected 10% by Q4. | Automate inventory tracking; renegotiate contracts with top three suppliers.
4 | Increase Sales Revenue from E-Commerce | To grow e-commerce revenue by 25% through improved UX and mobile optimization. | 2025-11-30 | Lisa Chen | Not Started | Current e-commerce revenue: $800K → Target: $1M. | Redesign mobile website; implement A/B testing for checkout flow.
5 | Launch New Product Line in Q3 | To introduce a sustainable product line and capture 10% of the eco-conscious segment. | 2025-09-15 | David Taylor | Preparation Phase | Product design finalized; prototype tested. | Finalize manufacturing partnerships; conduct beta testing with 500 customers.