## Worksheet
Goal ID | Goal Description | Owner | Target Date | Current Status | Progress (%) | Key Milestones | Risk Assessment | Next Action Step | Notes
G-001 | Increase customer retention by 20% in Q3 | Sarah Johnson | 2024-07-31 | In Progress | 65% | Q3 Week 2: Survey launch Q3 Week 6: Feedback review | Low - Data collection delays | Launch retention campaign in Week 4 | Include incentives for long-term clients.
G-002 | Launch new CRM feature by end of Q2 | David Lee | 2024-06-30 | On Track | 85% | Beta testing - Week 3 Public launch - Week 8 | Medium - Integration issues | Finalize integration with existing modules | Ensure compliance with data privacy standards.
G-003 | Improve response time to customer inquiries | Lisa Chen | 2024-08-15 | Not Started | 0% | Review current process Train new support team | High - Staff turnover | Hire two additional support staff by June 10 | Target response time below 2 hours.
G-004 | Expand client outreach to new market segment | Mike Thompson | 2024-10-31 | Planning Phase | 15% | Market research phase Initial pilot campaign | Low - Market interest uncertain | Complete market analysis by July 15 | Focus on demographic groups aged 30–45.