## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible Person | Dependencies
Define Long-Term Vision | 2024-03-01 | 2024-03-15 | 15 | 100 | CEO | -
Set Annual Goals | 2024-03-16 | 2024-04-10 | 35 | 75 | Operations Director | Define Long-Term Vision
Break Down Goals into Quarterly Objectives | 2024-04-11 | 2024-06-30 | 90 | 50 | Strategy Team | Set Annual Goals
Conduct Performance Reviews | 2024-07-01 | 2024-07-31 | 31 | 85 | HR Manager | Break Down Goals into Quarterly Objectives
Review and Adjust Goals (Mid-Year) | 2024-08-15 | 2024-08-31 | 17 | 60 | CEO & Strategy Team | Conduct Performance Reviews
Finalize and Communicate Annual Goals | 2024-09-01 | 2024-09-30 | 30 | 100 | All Leadership Team | Review and Adjust Goals (Mid-Year)