## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Progress (%)
Define Strategic Goals | 2024-03-01 | 2024-03-15 | 15 | CEO & Strategy Team | 100%
Conduct Market Research | 2024-03-16 | 2024-04-10 | 35 | Marketing Director | 75%
Develop Action Plan | 2024-04-11 | 2024-05-31 | 61 | Operations Manager | 40%
Budget Allocation & Approval | 2024-06-01 | 2024-06-15 | 15 | Finance Officer | 90%
Launch Pilot Program | 2024-06-16 | 2024-08-31 | 76 | Product Team & Field Managers | 0%