## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Progress (%) | Status | Dependencies | Milestones
Define Goal Objectives | 2024-04-01 | 2024-04-10 | 10 | Jane Doe | 95% | Completed | None | Yes
Conduct Stakeholder Analysis | 2024-04-11 | 2024-04-18 | 8 | John Smith | 75% | In Progress | Depends on Objective Definition | No
Develop Action Plan | 2024-04-19 | 2024-05-03 | 15 | Alice Brown | 30% | Pending | Depends on Stakeholder Analysis | No
Allocate Resources & Budget | 2024-05-04 | 2024-05-15 | 12 | Robert Lee | 10% | Not Started | None | No
Monitor & Adjust Strategy | 2024-05-16 | 2024-06-30 | 45 | Jane Doe, John Smith | 0% | Not Started | Depends on Action Plan Completion | Yes