## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Status
Define Quarterly Goals | 2024-03-01 | 2024-03-15 | 15 | 85% | On Track
Conduct Team Workshops | 2024-03-16 | 2024-03-25 | 10 | 60% | In Progress
Set Individual KPIs | 2024-03-26 | 2024-04-10 | 15 | 30% | Planned
Review and Adjust Goals | 2024-04-11 | 2024-04-18 | 8 | 0% | Not Started
Finalize Goal Documentation | 2024-04-19 | 2024-05-03 | 15 | 10% | Planned