## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible | Status | Dependencies
Define Long-Term Vision | 2024-01-01 | 2024-01-15 | 15 | 85% | Jane Doe | On Track | None
Set SMART Goals | 2024-01-16 | 2024-01-31 | 25 | 70% | John Smith | In Progress | Define Vision
Develop Action Plan | 2024-02-01 | 2024-03-31 | 60 | 35% | Lisa Chen | Planning | SMART Goals
Monitor & Review Progress | 2024-04-01 | 2024-12-31 | 365 | 0% | Team Lead | Not Started | Action Plan & Goals
Adjust Goals & Strategies | 2025-01-01 | 2025-03-31 | 90 | 0% | Jane Doe | Not Started | Progress Review