## Worksheet
Task | Start Date | End Date | Duration | Responsible Party | Status
Define Strategic Goals | 2024-03-01 | 2024-03-15 | 15 days | Executive Leadership Team | On Track
Market Research & Analysis | 2024-03-16 | 2024-04-10 | 35 days | Business Intelligence Unit | In Progress
Product Roadmap Development | 2024-04-11 | 2024-05-31 | 60 days | Product Management Office | Planned
Budget Allocation & Funding | 2024-05-01 | 2024-05-30 | 30 days | Finance Department | Pending Approval
Team Training & Onboarding | 2024-06-01 | 2024-06-30 | 30 days | HR & Operations Team | Not Started
Launch Planning Workshop | 2024-07-01 | 2024-07-15 | 15 days | Project Steering Committee | In Planning