## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible
Define Project Goals | 2024-03-01 | 2024-03-05 | 5 | Completed | John Doe
Conduct Stakeholder Analysis | 2024-03-06 | 2024-03-15 | 10 | In Progress | Jane Smith
Develop Goal Framework | 2024-03-16 | 2024-03-25 | 10 | Planned | Alex Johnson
Review and Finalize Goals | 2024-03-26 | 2024-03-31 | 6 | Pending | Team Lead
Communicate Goals to Team | 2024-04-01 | 2024-04-03 | 3 | Not Started | Marketing Director