## Worksheet
Task | Start Date | End Date | Duration (Days) | Status
Define Long-Term Goals | 2024-03-01 | 2024-03-15 | 15 | Completed
Break Down Goals into Milestones | 2024-03-16 | 2024-04-10 | 35 | In Progress
Set Weekly Action Plan | 2024-04-11 | 2024-05-31 | 61 | Not Started
Review Progress Biweekly | 2024-05-01 | 2024-06-30 | 61 | Not Started
Adjust Goals Based on Feedback | 2024-07-01 | 2024-07-31 | 31 | Not Started