## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Progress (%)
Define Project Vision | 2024-03-01 | 2024-03-05 | 5 | Strategy Team | 100
Market Research & Analysis | 2024-03-06 | 2024-03-15 | 10 | Research Team | 85
Product Requirements Specification | 2024-03-16 | 2024-03-25 | 10 | Product Team | 70
Development Phase (Phase 1) | 2024-03-26 | 2024-04-15 | 20 | Engineering Team | 50
User Testing & Feedback Loop | 2024-04-16 | 2024-04-30 | 15 | UX & QA Team | 30
Final Review & Go-Live Planning | 2024-05-01 | 2024-05-10 | 10 | Project & Operations Team | 10