## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible Person
Define Goals & Objectives | 2024-03-01 | 2024-03-05 | 5 | 100 | Sarah Johnson
Market Research & Analysis | 2024-03-06 | 2024-03-18 | 13 | 75 | Mike Thompson
Develop Strategy Plan | 2024-03-19 | 2024-04-01 | 13 | 50 | Lisa Chen
Implement Campaigns | 2024-04-02 | 2024-05-15 | 55 | 30 | David Ruiz
Monitor & Review Performance | 2024-05-16 | 2024-06-30 | 45 | 0 | Team Lead