## Worksheet
Goal Identifier | Goal Description | Objective (SMART) | Target Date | Responsible Person | Current Status | Progress % | Risk Assessment | Action Plan | Review Frequency | Inventory Items Involved (if any)
G-001 | Increase inventory turnover by 20% within the next fiscal year. | Specific: Improve stock rotation process; Measurable: Turnover rate to increase from 3.5 to 4.2; Achievable: With reorganization of warehouse layout; Relevant: Aligns with operational efficiency goals; Time-bound: By December 31, 2025. | December 31, 2025 | Jane Smith | On Track | 78% | Low – process optimization only | Reassess stock categorization monthly; implement FIFO tracking system. | Monthly | A1, B2, C3, D4 (high-turnover SKUs)
G-002 | Reduce obsolete inventory by 30%. | Specific: Identify and classify obsolete stock; Measurable: Reduce obsolete stock from 15% to 10.5%; Achievable: With vendor renegotiation and demand forecasting; Relevant: Minimizes capital lock-up; Time-bound: By September 30, 2025. | September 30, 2025 | Mark Johnson | In Progress | 45% | Medium – outdated supplier contracts | Conduct quarterly review of inventory age; initiate vendor re-evaluation by Q3. | Quarterly | E5, F6, G7 (low-demand items)
G-003 | Improve inventory accuracy to 99.5%. | Specific: Conduct weekly cycle counts; Measurable: Accuracy rate reaches 99.5%; Achievable: With staff training and automated systems; Relevant: Supports reliable reporting; Time-bound: By June 30, 2025. | June 30, 2025 | Sarah Lee | Not Started | 0% | Low – training and tools available | Train staff on inventory systems; implement barcode scanning by May 2025. | Bi-weekly | All warehouse zones (Z1-Z5)
G-004 | Establish safety stock levels for critical components. | Specific: Define buffer stocks based on demand variability; Measurable: Reduce stockouts by 50%; Achievable: Using historical data and forecasting tools; Relevant: Ensures supply chain continuity; Time-bound: By March 31, 2025. | March 31, 2025 | David Kim | On Track | 85% | Low – data is reliable and up to date | Finalize safety stock parameters in Q1; validate with procurement team. | Monthly | H8, I9 (critical electronics)