## Worksheet
Date | Goal Objective | Target Deadline | Current Progress (%) | Resources Required | Assigned To | Status | Remarks / Notes
2024-04-05 | Launch Q2 Marketing Campaign | 2024-06-30 | 65% | Budget: $15,000, Design Team, Content Writers | Sarah Chen | In Progress | Final designs due by May 15. Social media schedule in development.
2024-04-10 | Improve Customer Retention Rate | 2024-12-31 | 30% | Loyalty program design, CRM integration, Email automation tools | James Rivera | Pending Review | Initial survey results submitted. Feedback analysis pending.
2024-04-15 | Develop New Product Feature (AI Chatbot) | 2024-09-30 | 15% | Development team, UX Design, Backend API | Lena Park | Planning Phase | Feasibility study complete. MVP timeline under review.
2024-04-20 | Expand International Sales to EU | 2024-11-30 | 5% | Market research, Legal compliance, Localized content | Marcus Thompson | Pending Approval | Local partnerships being assessed. Regulatory requirements not finalized.