## Worksheet
Date | Goal Description | Objective (SMART) | Target Deadline | Current Progress | Responsible Person | Status (Pending/In Progress/Completed) | Notes / Observations | Review Date | Action Plan for Next Phase
2024-04-01 | Improve team communication efficiency | Establish weekly stand-up meetings to enhance transparency and collaboration. | 2024-06-30 | Started weekly meetings; 3/5 sessions completed. | Jane Smith | In Progress | Participants report increased clarity in task allocation. | 2024-05-15 | Introduce feedback forms post-meetings to assess effectiveness.
2024-03-15 | Enhance customer satisfaction scores | Reduce average response time to customer inquiries to under 2 hours. | 2024-12-31 | Response time reduced from 4.5h to 1.8h (current). | John Doe | Completed | Satisfaction survey results show +25% improvement. | 2024-03-31 | N/A – goal achieved.
2024-05-10 | Update project management tools | Migrate to a unified platform with real-time collaboration features. | 2024-07-15 | Tool evaluation completed; migration phase scheduled. | Lisa Chen | Pending | Team requires training on new interface. | 2024-06-10 | Arrange training sessions and assign a support lead.