## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Milestone | Resources Required | Dependencies | Progress (%)
Define Project Vision & Goals | John Smith | 2024-03-01 | 2024-03-15 | Completed | High | Vision Finalized | Stakeholder Workshops, Strategy Team | None | 100%
Develop Detailed Project Plan | Sarah Lee | 2024-03-16 | 2024-04-05 | In Progress | High | Plan Approved | Project Manager, Finance, Ops | Vision Finalized | 65%
Conduct Risk Assessment & Mitigation | Michael Chen | 2024-04-06 | 2024-04-18 | Not Started | Medium | Risk Register Ready | Risk Analyst, Legal Review | Project Plan Approved | 0%
Secure Stakeholder Buy-In | Lisa Wong | 2024-04-19 | 2024-05-03 | Planned | High | Stakeholder Agreement Signed | Executive Team, Marketing, HR | Risk Assessment Complete | 0%
Finalize Budget & Resource Allocation | David Patel | 2024-05-04 | 2024-05-15 | Not Started | Medium | Budget Approved | Finance, HR, IT | Stakeholder Buy-In Secured | 0%