## Worksheet
Task | Goal | Owner | Start Date | End Date | Status | Priority | Milestone
Define Project Objectives | Establish clear, measurable goals for the project. | Jane Smith | 2024-01-15 | 2024-01-31 | In Progress | High | Objective Approval
Conduct Stakeholder Analysis | Identify and map key stakeholders and their interests. | Mark Johnson | 2024-02-01 | 2024-02-14 | Not Started | Medium | Stakeholder Map Complete
Develop Project Timeline | Create a detailed schedule with task dependencies. | Lisa Chen | 2024-02-15 | 2024-03-01 | Planned | High | Timeline Finalized
Secure Budget Approval | Obtain financial authorization from executive team. | David Brown | 2024-03-05 | 2024-03-15 | Not Started | High | Budget Approved
Kickoff Meeting | Hold initial project launch meeting with all teams. | Team Lead | 2024-03-20 | 2024-03-20 | Scheduled | Medium | Project Launched