## Worksheet
Project Name | Goal Statement | Objective (SMART) | Key Milestones | Timeline (Start - End) | Responsible Party | Status | Progress % | Next Action Step
Website Redesign Project | Improve user engagement by increasing site traffic by 40% within six months. | Specific, Measurable, Achievable, Relevant, Time-bound — Increase monthly visits to 15K by Q4 2024. | Requirement Gathering – March 2024 Wireframing & UX Approval – April 2024 Development Launch – June 2024 | March 1, 2024 – June 30, 2024 | Marketing & Product Team | On Track | 75% | Finalize content strategy and conduct user testing in May.
Client Onboarding Process | Ensure new clients are onboarded within 5 business days of signing contract. | All onboarding steps completed in a consistent, documented workflow with client feedback collected weekly. | Contract Review – Immediate Client Portal Setup – Day 1 Orientation Meeting – Day 2 | Day 0 – Day 5 | Onboarding Specialist | Completed | 100% | Begin optimization for first client feedback review.
Content Marketing Strategy | Generate at least 30 high-quality blog posts per quarter to improve SEO and brand visibility. | Publish 25 articles by Q2, achieve top-5 ranking for three core keywords. | Topic Planning – Jan Content Calendar Finalized – Feb First Batch Published – Mar | January 2024 – December 2024 | Content Manager | On Track | 60% | Finalize Q2 topics and schedule publishing for April.