## Worksheet
Task | Objective | Start Date | End Date | Responsible Person | Status | Progress (%)
Define Project Scope | Clarify project goals, deliverables, and boundaries | 2024-03-01 | 2024-03-15 | Jane Doe | Completed | 100
Develop Project Plan | Create detailed timeline, milestones, and resources needed | 2024-03-16 | 2024-04-05 | John Smith | In Progress | 75
Secure Stakeholder Approval | Obtain formal sign-off from key stakeholders | 2024-04-06 | 2024-04-15 | Sarah Lee | Not Started | 0
Execute Project Activities | Begin implementation of project deliverables | 2024-04-16 | 2024-06-30 | Team A | Not Started | 0
Monitor & Review Progress | Conduct weekly reviews to assess performance and adjust plans as needed | 2024-05-01 | 2024-06-30 | Michael Brown | Not Started | 0
Finalize Deliverables & Close Project | Complete final documentation, handover, and close project formally | 2024-07-01 | 2024-07-15 | Jane Doe | Not Started | 0