## Worksheet
Task | Objective | Start Date | End Date | Responsible Person | Resources Required | Milestones | Dependencies | Risks & Mitigation | Status
Project Initiation | Define project scope, goals, and key stakeholders. | 2024-03-01 | 2024-03-15 | Project Manager | Stakeholder meetings, scope document, budget draft | Finalize project charter |  | Unclear stakeholder needs – conduct early workshops. | In Progress
Market Research | Analyze target audience and competitive landscape. | 2024-03-16 | 2024-04-05 | Market Analyst | Surveys, interviews, tools (e.g., Google Forms, SEMrush) | Data collected and insights report ready | Project Initiation completed | Data delays – have backup data sources. | Planned
Product Design | Develop wireframes and prototypes based on user insights. | 2024-04-06 | 2024-05-10 | UX/UI Designer | Design software (Figma), user testing tools | Prototype approved by stakeholders | Market Research completed | User feedback cycle too long – schedule iterative review. | In Progress
Development Phase | Build core functionality according to design specs. | 2024-05-11 | 2024-07-30 | Software Engineers | Servers, development environment, codebase tools | Alpha version deployed internally | Product Design finalized | Technical debt – prioritize refactoring in sprint 3. | Planned
Testing & Quality Assurance | Conduct unit, integration, and user acceptance testing. | 2024-08-01 | 2024-08-25 | QA Lead | Testing tools, test cases, feedback forms | Bug resolution rate >95% | Development phase completed | Critical bugs discovered late – improve testing early. | Planned
Launch & Rollout | Deploy product to public market with marketing campaign. | 2024-08-26 | 2024-09-15 | Marketing Director | Launch website, social media, email lists | First 100 users active within first week | Testing & QA completed | Marketing budget exceeded – reallocate in post-launch. | Planned
Post-Launch Review | Evaluate performance, user feedback, and plan improvements. | 2024-09-16 | 2024-09-30 | Project Manager & Team | Analytics tools, feedback surveys | Final project report and roadmap for Q4 | Launch completed | Low user engagement – investigate onboarding process. | Planned