## Worksheet
Task | Objective | Goal | Timeline | Owner | Resources Required | Milestones | Risks & Dependencies | Status | Progress (%)
Project Initiation | Define project scope and objectives | Secure buy-in from stakeholders and finalize project vision | Week 1–2 | Project Manager | Stakeholder meetings, scope document | Scope approval received | Stakeholder resistance, unclear vision | On Track | 80%
Market Research | Analyze market trends and customer needs | Identify key customer segments and preferences | Week 3–5 | Research Lead | Surveys, focus groups, data tools | Data collection complete | Low response rate in target group | On Track | 75%
Product Design | Develop initial product concepts and wireframes | Deliver 3 viable design options for review | Week 6–8 | UX Designer | Design software, user feedback tools | Design proposals submitted | Feedback delay from stakeholders | On Track | 60%
Development Phase | Build product prototype and core functionality | Complete functional prototype with testing suite | Week 9–14 | Development Team | Code repositories, servers, QA tools | Prototype ready for testing | Technical debt issues, integration delays | On Track | 50%
Testing & Validation | Validate product performance and usability | Achieve 95% user satisfaction in testing phase | Week 15–16 | QA Lead | Test cases, user feedback forms, analytics tools | Final test report approved | Critical bugs found post-testing | On Track | 90%
Launch & Rollout | Deploy product to end users and begin operations | Achieve 10,000 active users within first month | Week 17–20 | Marketing Director | Launch campaign, support team, monitoring tools | Official launch date set | User adoption slower than projected | On Track | 40%