## Worksheet
Task | Objective | Target Milestone | Budget Allocation ($) | Resource Required | Timeline (Months) | Status
Market Research & Analysis | Identify target audience and market trends | Month 1 | 5,000 | Research Team, Analytics Tools | 1 | On Track
Product Development Phase | Design and prototype final product | Month 3 | 20,000 | Engineering Team, UX Designers | 3 | In Progress
Pilot Testing & Feedback Loop | Validate product with selected users | Month 5 | 8,000 | Beta Testers, QA Team | 2 | Planned
Full Scale Launch | Roll out product to public market | Month 7 | 50,000 | Marketing, Sales, Operations | 4 | Not Started
Post-Launch Performance Review | Assess ROI and user engagement | Month 10 | 10,000 | Finance Team, Analytics Team | 3 | Planned