## Worksheet
Project Phase | Goal Statement | Key Objectives | Target Audience | Timeline (Months) | Responsible Team | Key Deliverables | Success Metrics
Initiation | Define strategic business objectives and align with organizational vision. | - Conduct stakeholder analysis - Identify market gaps - Validate feasibility | Executive Leadership, Strategy Committee | 1 | Strategic Planning Team | - Vision document - Market analysis report - Feasibility study | - Stakeholder buy-in rate ≥85% - Clear alignment with strategic priorities
Planning | Develop detailed project roadmap and resource allocation plan. | - Define scope and constraints - Estimate budget and timeline - Identify risks and mitigation strategies | Project Management Office (PMO) | 2 | Project Steering Committee | - Project charter - Detailed work breakdown structure (WBS) - Risk register | - Approved project plan - Budget variance <5% - Risk coverage ≥90%
Execution | Implement the project plan with defined milestones and accountability. | - Execute tasks per timeline - Monitor team performance - Conduct regular reviews | Project Teams, Department Heads | 4 | Cross-functional Project Team | - Milestone reports - Weekly performance dashboards - Process documentation | - On-time delivery rate ≥95% - Team productivity index ≥80%
Review & Optimization | Assess outcomes, gather feedback, and refine processes for future projects. | - Conduct post-project evaluation - Gather stakeholder feedback - Document lessons learned | All Stakeholders, Quality Assurance Team | 1 | Project Retrospective Group | - Post-project review report - Lessons learned repository - Process improvement plan | - Satisfaction score ≥4.5/5 - Identified process improvements ≥3