## Worksheet
Project Name | Goal Statement | Timeline (Start – End) | Key Milestones | Owner | Status | Progress (%)
Q4 Growth Initiative | Increase market share by 15% within the next quarter through targeted campaigns. | October 01 – December 31, 2024 | Market research completed (Nov 05) Campaign launch (Dec 01) Performance review (Dec 25) | Sarah Johnson | On Track | 85%
Product Launch – Nova X | Launch a new AI-powered product by Q2 to capture tech-savvy customer segment. | January 05 – April 30, 2025 | Prototype finalized (Jan 30) Internal testing completed (Feb 28) Customer beta launch (March 15) | David Chen | In Progress | 50%
Team Expansion & Training | Expand team by 5 members and complete onboarding and training by end of Q3. | July 01 – September 30, 2024 | Recruitment completed (Aug 15) Onboarding process launched (Aug 20) Training completion verified (Sept 28) | Lisa Martinez | Completed | 100%
Customer Retention Strategy | Improve retention rate by implementing personalized engagement programs. | March 01 – June 30, 2025 | Segmentation analysis done (Mar 15) Engagement pilot launched (Apr 05) Full rollout scheduled (May 31) | Michael Turner | Planned | 0%