## Worksheet
Month | Project Goal | Key Objectives | Milestones | Responsible Person | Due Date | Status | Progress (%)
January | Complete project kickoff and finalize scope | Define deliverables, set timelines, engage stakeholders | Finalize project charter Conduct stakeholder meeting | J. Smith | 2024-01-31 | Completed | 100%
February | Develop initial project plan and budget | Create WBS, estimate costs, assign resources | Finalize work breakdown structure Approve budget draft | A. Johnson | 2024-02-28 | In Progress | 75%
March | Begin prototype development | Design UI/UX, build core functionality | Complete wireframes Develop MVP version | M. Brown | 2024-03-31 | Not Started | 0%
April | Conduct user testing and gather feedback | Test with target users, collect insights | Host beta testing session Generate feedback report | L. Davis | 2024-04-30 | Planned | 0%
May | Finalize product and prepare launch | Review feedback, polish features, finalize marketing | Release final product version Launch marketing campaign | T. Wilson | 2024-05-31Not Started | 0%