## Project Plan - Goal Setting
Project Plan – Goal Setting
Goal Statement | Objective (Specific) | Key Performance Indicators (KPIs) | Target Date | Responsible Person | Status | Risks & Challenges th> | Action Plan & Milestones th>
Improve customer satisfaction by 20% within the next fiscal year. | Conduct quarterly surveys to gather feedback and implement changes based on results. | Customer Satisfaction Score (CSAT) ≥ 85%, Net Promoter Score (NPS) ≥ 70% | Dec 31, 2024 | Jane Smith | Active | Survey response bias; slow response time from support team | Q1: Launch survey; Q2: Analyze data; Q3: Implement changes; Q4: Review results
Launch new digital marketing campaign. | Achieve 10,000 new website visits per month by end of Q3. | Monthly traffic: ≥10,000; Conversion rate: ≥2.5% | Sep 30, 2024 | Mark Johnson | Pending Approval | Lack of budget; unclear target audience | Finalize campaign design in Q1; approve budget by Q2; launch in Q3
Reduce operational costs by 15% over the next 12 months. | Identify and eliminate redundant processes and optimize supply chain logistics. | Cost reduction: ≥15%; Monthly savings: $20,000 | Sarah Lee | Planning | Resistance from team members; data accuracy issues in current cost reports | Conduct process audit (Q1); present findings (Q2); implement changes (Q3)