## Worksheet
Task/Activity | Owner | Start Date | End Date | Status | Progress (%) | Notes/Remarks
Define Project Goals and Objectives | John Smith | 2024-03-15 | 2024-03-18 | Completed | 100% | Aligned with organizational strategy and stakeholder expectations.
Conduct Stakeholder Analysis | Sarah Johnson | 2024-03-19 | 2024-03-25 | In Progress | 65% | Initial interviews completed; final report due by 3/28.
Develop Detailed Project Plan | Michael Lee | 2024-03-26 | 2024-04-05 | Pending | 0% | Draft version ready for review.
Allocate Resources and Budget | Emily Chen | 2024-04-06 | 2024-04-12 | Pending | 0% | Budget approval pending from Finance Department.
Set Milestones and Key Performance Indicators (KPIs) | James Wilson | 2024-04-13 | 2024-04-20 | Pending | 0% | To be finalized after stakeholder feedback.