## Worksheet
Project Name | Goal Statement | Target Date | Key Milestones | Responsible Person | Budget (USD) | Status
Launch Social Media Campaign | Increase brand awareness by 30% within the first quarter. | March 31, 2024 | Content creation (Weeks 1-4) Launch (Week 5) Performance review (Week 8) | Sarah Johnson | $2,500 | On Track
Develop New Product Line | Introduce two new eco-friendly products by end of Q3. | September 15, 2024 | Market research (Weeks 1-3) Design phase (Weeks 4-6) Prototype testing (Week 7) | David Chen | $15,000 | Planning
Customer Retention Program | Improve customer retention rate by 15% in 6 months. | June 30, 2024 | Surveys and analysis (Weeks 1-2) Program rollout (Weeks 3-5) Feedback collection (Week 6) | Lisa Martinez | $4,200 | In Progress
Website Redesign | Improve user experience and increase conversion rate by 20%. | May 30, 2024 | UX audit (Week 1) Design mockups (Weeks 2-3) Development & testing (Weeks 4-6) | Mike Rodriguez | $8,000 | Scheduled