## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes / Goals
Define Project Vision & Objectives | Project Lead | 2024-04-01 | 2024-04-15 | In Progress | 60% | None | Align team on long-term goals and success metrics.
Conduct Stakeholder Analysis | Business Analyst | 2024-04-16 | 2024-04-28 | On Track | 100% | Vision Definition Complete | Identify key stakeholders and their priorities.
Develop Initial Project Plan | Project Manager | 2024-04-29 | 2024-05-10 | Not Started | 0% | Stakeholder Analysis Complete | Outline deliverables, timelines, and milestones.
Team Kickoff & Goal Alignment Meeting | Team Lead | 2024-05-11 | 2024-05-11 | Planned | 0% | Project Plan Draft Available | Ensure all team members understand project goals and roles.