## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Priority | Notes
Define Project Goals | Alice Smith | 2024-03-15 | 2024-03-20 | Completed | 100% | High | Clear objectives aligned with strategic vision.
Conduct Stakeholder Analysis | Bob Johnson | <2024-03-212024-04-05 | In Progress | 65% | Medium | Identifying key stakeholders and their interests.
Develop Project Timeline | Carol Lee | 2024-04-06 | 2024-04-15 | Not Started | 0% | High | Create Gantt chart based on milestones.
Allocate Budget | David Kim | 2024-04-16 | 2024-04-20 | Not Started | 0% | Medium | Finalize cost breakdown by department.
Review & Approve Plan | Project Manager | 2024-04-21 | 2024-04-25 | Not Started | 0% | High | Final sign-off before execution begins.