## Worksheet
Week | Project Goal | Key Actions | Resources Needed | Timeline (Days) | Owner | Status
1 | Define project scope and objectives | Conduct stakeholder interviews, draft goal document | Stakeholder list, meeting room, notes template | 7 | Alex Johnson | In Progress
2 | Finalize project timeline and milestones | Map workflow, set key deadlines, review with team | Project management tool (e.g., Trello), calendar access | 5 | Sam Rivera | Planned
3 | Assign roles and responsibilities | Create RACI chart, communicate assignments | Team roster, communication platform (Slack/Teams) | 3 | Taylor Chen | Pending Approval
4 | Conduct risk assessment and mitigation planning | Identify risks, develop response strategies, document plan | Risk matrix template, project data | 7 | Jordan Lee | Scheduled
5 | Launch first phase of development | Begin prototype design, initiate user testing | Design tools, user feedback forms | 10 | Mia Patel | On Track