## Worksheet
Project Name | Goal Statement | Target Date | Key Milestones | Responsible Party | Status
Website Redesign Project | Improve user experience and increase conversion rates by 30% within six months. | 2024-12-31 | Phase 1: Research & Analysis (Completed) Phase 2: Wireframing (In Progress) Phase 3: Design Finalization (Scheduled) | Marketing Team | On Track
Client Onboarding Process | Streamline onboarding to reduce client setup time by 50% within the first quarter. | 2024-09-30 | Step 1: Workflow Documentation (Completed) Step 2: Training Module Development (In Progress) | Operations Team | On Track
Mobile App Launch | Launch a fully functional mobile app with at least 5,000 active users by Q3. | 2024-07-15 | Beta Testing (Scheduled) App Store Submission (Pending) | Product & Dev Teams | At Risk
Customer Feedback System | Implement a digital feedback system to collect and analyze customer insights monthly. | 2024-08-31 | System Design (Completed) Integration with CRM (In Progress) | Customer Success Team | On Track
Brand Identity Refresh | Develop a modern, inclusive brand identity that reflects our values and targets new markets. | 2024-10-30 | Research & Strategy (Completed) Design Concepts (In Progress) | Creative Team | On Track