## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Milestones | Dependencies
Define Project Vision & Objectives | Marketing Director | 2024-03-01 | 2024-03-15 | Completed | High | Vision approved, Stakeholder alignment achieved | None
Conduct Market Research & Analysis | Research Manager | 2024-03-16 | 2024-04-10 | In Progress | High | Data collection complete, Report draft ready | Vision approval
Develop Project Timeline & Roadmap | Project Lead | 2024-04-11 | 2024-04-30 | Planned | Medium | Timeline finalized, Key phases identified | Market research report
Finalize Budget & Resource Allocation | Finance Manager | 2024-05-01 | 2024-05-15 | Pending | High | Budget approved, Teams assigned | Project timeline approved
Launch Pilot Phase | Product Team | 2024-06-01 | 2024-06-30 | Not Started | High | Pilot feedback collected, Metrics tracked | Budget finalized, Timeline approved
Full-Scale Rollout & Monitoring | Operations Lead | 2024-07-01 | 2024-10-31 | Planned | Medium | Monthly reviews, KPI dashboards active | Pilot phase completed
Project Timeline & Goal Setting – Advanced Version